## Risk Tracking Template
Risk Tracking
Date of last review: 10/05/2023
ID | Description of Risk | Impact | Risk Reponse | Risk Level | Risk owner | Notes
1 | Supplier delay for website hosting or tools | Pushes website launch | Confirm delivery dates by Phase 2 | High | Team 6 | SAMPLE
2 | Lack of clarity about types of distress | Misclassification or misinterpretation of user's distress | Develop a robust classification system with expert input | High | Team 6 | Requires expert consultation.
3 | User data breach | Privacy concerns and potential legal actions | Implement robust security measures | Very High | Team 6 | Ensure GDPR compliance
4 | Website crashes due to high traffic | Service disruption | Invest in scalable hosting solution | Medium | Team 6 | Monitor website traffic and adjust accordingly
5 | Inaccurate distress relief solutions | Could exacerbate user's distress | Continuously update and vet resources | High | Team 6 | Collaborate with professionals
6 | Ineffective website user interface | Users find it hard to navigate or understand resources | Regularly gather user feedback and refine design | Medium | Team 6 | UI/UX designer to be consulted
7 | Not reaching the target audience effectively | Reduced website traffic and effectiveness | Develop and refine marketing strategies | Medium | Team 6 | Consider social media campaigns
8 | Regulatory compliance issues | Legal repercussions and fines | Stay updated on local and international laws pertaining to distress relief | High | Team 6 | Ensure constant legal review
9 | Miscommunication among team members | Delays and errors in website development | Regular team meetings and clear documentation | Low | Team 6 | Consider collaboration tools
10 | Incomplete or inaccurate forms on 'Apply Now/Contact Us' page | Users may not receive appropriate help | Regularly review and refine forms | Medium | Team 6 | Ensure clarity in instructions
11 | Website not mobile-responsive | Limited accessibility for mobile users | Ensure mobile-first design approach | Medium | Team 6 | Regular testing on various devices
12 | Negative feedback or reviews from users | Damaged reputation and reduced user trust | Address feedback promptly and make necessary adjustments | Medium | Team 6 | Monitor user reviews consistently
13 | Overdependence on a single external resource | Users might not get diverse solutions | Ensure multiple vetted sources per distress type | Medium | Team 6 | Regularly scout for new credible resources
14 | Outdated information on the 'Information page' | Users might receive outdated solutions | Schedule regular content updates | Medium | Team 6 | Engage industry experts for updates
15 | Insufficient training for representatives handling user queries | Users might not get accurate assistance | Conduct regular training sessions | High | Team 6 | Engage professionals for training
16 | Website load speed issues | Users might leave the site due to impatience | Optimize images, scripts, and hosting solution | Medium | Team 6 | Regular site speed testing
17 | Unplanned costs in website development | Strain on project budget | Regular budget review and contingency planning | Medium | Team 6 | Track all expenses meticulously
18 | Home page delay | Pushes launch | Make sure to finish within correct sprint | High | Team 6 | Without home page we don't have anything
19 | Information page delay | Pushes launch | Make sure to finish within correct sprint | High | Team 6 | Without information page wont be able to identify different areas of distress
20 | About us page delay | Pushes launch | Make sure to finish within correct sprint | High | Team 6 | Without the page information about us will not be provided
21 | Contact page delay | Pushes launch | Make sure to finish within correct sprint | High | Team 6 | Without the page people will not be able to contact the correct distress line
22 | Donation page delay | Pushes launch | Make sure to finish within correct sprint | Medium | Team 6 | Will not be able to offer help out
23 | Team member sick | Slows production | Online communication | Low | Affected team member | Get well soon hopefully
24 | Data Breach | Reputation, Lost of private data | apoligize and strengthen security | High | Security Team | Hopefully this wont happen because we will prepare
25 | High Traffic | Slows Site | Increase server size to hadle more traffic | Medium | Servere Team | Pick a good server
26 | Low funding | Pushes launch | Get Donations/investors | High | Fincial Team | Have enough money before starting to not get behind
27 | Fincial Crime | Reputation, Lost of private data | Lawsuit against hacker | High | Security Team | Choose good payment security
28 | Attact from hacker | Website down, lost of private data | Lawsuit against hacker and recover | High | Security Team | Hire more security team
29 | Project lead changes requiments | Pushes launch | Work on new changes | Medium | Team 6 | Make sure on the same page with project lead
30 | Empolyee sabotage | Destroy launch | Fire empolyee | High | Team 6 | Check eachother work
31 | Hardware malfunction | Delays launch | Buy new machine | Low | Team member | You can use campus comptures
32 | Software malfunction | Delays launch | Update software | Low | Team member | Make sure software is up to date

## How to Use this Template
Introduction
A risk tracking template allows you to identify and track any risks that might appear in your project. It's critical to track risks in your projects, so they don't become issues that derail progress. A risk tracking template is a living document, and should be frequently inspected and updated.
Definition of Terms
ID: The identification number of your risk.
Description of Risk: Provide a brief description of your risk that anyone can understand.
Impact: Outline the potential impact that risk can have on your project.
Risk Response: Describe what your reaction to the risk is, in order to quell it.
Risk Level: Define the priority of the risk; how likely it is to affect your project.
Risk Owner: Define the team member or manager in charge of monitoring the risk.
Notes: Add any notes you may have for a better understanding of the risk. Update regularly.