## Risk Tracking Template
Risk Tracking Template
Date of last review:
ID | Description of Risk | Impact | Risk Reponse | Risk Level | Risk owner | Notes
1 | Home page delay | Pushes launch | Make sure to finish within correct sprint | High | Team 6 | Without home page we don't have anything
2 | Information page delay | Pushes launch | Make sure to finish within correct sprint | High | Team 6 | Without information page wont be able to identify different areas of distress
3 | About us page delay | Pushes launch | Make sure to finish within correct sprint | High | Team 6 | Without the page information about us will not be provided
4 | Contact page delay | Pushes launch | Make sure to finish within correct sprint | High | Team 6 | Without the page people will not be able to contact the correct distress line
5 | Donation page delay | Pushes launch | Make sure to finish within correct sprint | Medium | Team 6 | Will not be able to offer help out
6 | Team member sick | Slows production | Online communication | Low | Affected team member | Get well soon hopefully
7 | Data Breach | Reputation, Lost of private data | apoligize and strengthen security | High | Security Team | Hopefully this wont happen because we will prepare
8 | High Traffic | Slows Site | Increase server size to hadle more traffic | Medium | Servere Team | Pick a good server
9 | Low funding | Pushes launch | Get Donations/investors | High | Fincial Team | Have enough money before starting to not get behind
10 | Fincial Crime | Reputation, Lost of private data | Lawsuit against hacker | High | Security Team | Choose good payment security
11 | Attact from hacker | Website down, lost of private data | Lawsuit against hacker and recover | High | Security Team | Hire more security team
12 | Project lead changes requiments | Pushes launch | Work on new changes | Medium | Team 6 | Make sure on the same page with project lead
13 | Empolyee sabotage | Destroy launch | Fire empolyee | High | Team 6 | Check eachother work
14 | Hardware malfunction | Delays launch | Buy new machine | Low | Team member | You can use campus comptures
15 | Software malfunction | Delays launch | Update software | Low | Team member | Make sure software is up to date
Related Free Templates
Dashaboard Template
Issue Tracking Template
Change Log Template

## How to Use this Template
Introduction
A risk tracking template allows you to identify and track any risks that might appear in your project. It's critical to track risks in your projects, so they don't become issues that derail progress. A risk tracking template is a living document, and should be frequently inspected and updated.
Definition of Terms
ID: The identification number of your risk.
Description of Risk: Provide a brief description of your risk that anyone can understand.
Impact: Outline the potential impact that risk can have on your project.
Risk Response: Describe what your reaction to the risk is, in order to quell it.
Risk Level: Define the priority of the risk; how likely it is to affect your project.
Risk Owner: Define the team member or manager in charge of monitoring the risk.
Notes: Add any notes you may have for a better understanding of the risk. Update regularly.