## Risk Matrix
Project Name: |  | Project Manager | Date
Distress relief system |  | Cedric | 2023-10-05
Risk Matrix |  | Severity |  |  |  |  | Related Free Templtes
IT Risk Assessment Template
|  | Insignificant | Minor | Moderate | Major | Severe+K10:P21 | Risk Register Template
Action Plan Template
Likelihood | Almost Certain | Syntax error | Server error | Data handling issue | Project lead changes requirments | Front end and back end connection error
| Likely | Can't meet in person | Inaccurate distress relief solution | Lack of clarity about distress | Stay cold of funding | Attact from hacker
| Possible | Team member sick | High traffic | Unplanned costs in website development | Financial Crime | User date breach
| Unlikelyh | Overdependence on a single external resource | Ineffective website user interface | Not reaching the target audience effectively | Regulatory compliance issue | Empolyee sabotage
| Rare | Negtive feekback or reviews from users | Compability | Hardware malfunction | Software malfunction | Pages delay

## Risk Matrix Key
Likelihood: Chance of risk
Rare: Slim possibility of happening
Unlikely: Could occur but remote
Possible: Might happen
Likely: Expected to occur
Almost Certain: Expected regularly
Severity: Impact on project
Insignificant: Not worth worry about
Minor: Can cause delays or added costs
Moderate: Likely delays or costs
Major: Possible failure
Severe: Definite failure
Risk Level: Setting Priority
Low: Not much risk
Medium: Some risk
High: Major risk
Very High: Extreme risk